## Slide 1: We welcome Danish market into NBS settlement!
Commissioning plan for Denmark integration
Tuomas Pulkkinen ı 06.05.2020

## Slide 2: Agenda
Overall Time Plan
Testing Activities
Structure Establishment and Management
Agreements
Communication and Documentation
New Features

## Slide 3: Overall Time Plan

## Slide 4: Go-Live in Two Phases
01.10.2020 – First go-live
eSett will take over calculation and invoicing of capacity reserves in Denmark
No impact on imbalance settlement
Concerns only about 10 BRPs that are active in capacity reserve market in Denmark
01.02.2021 – Second go-live
eSett will take over calculation and invoicing of imbalance settlement and activated reserves in Denmark
All similar operations as in other countries
Go-live for whole Danish market

## Slide 5: Testing Activities

## Slide 6: Testing Activities
eSett Test Environment
eSett Production Environment
5b. Parallel settlement
Testing activities (TSO / Datahub)
Testing activities (BRP)
Parallel run
Parallel run (mandatory)
3a. ONLS access
5a.*
1a. & 1b. Connectivity & data flow test
1c. E2E
2a.
2c. E2E test
2b. Data flow test
3d. BRP E2E test
3b. Connectivity
3c. Data flow test
3e.
3e.*
3. ONLS access & connectivity

## Slide 7: Involved Parties
eSett
Testing is carried out in eSett’s test environment
Energinet
Implementation of new functionalities and testing towards eSett
  Testing starts already in May
Focus in the beginning is in the capacity reserves
Energinet DataHub
Implementation of new functionalities and testing towards eSett
  Testing starts in August
Represents all Danish DSOs
BRPs
Online Service and data flow testing
  Testing can start already in May
  Focus on BRPs that are not active in Finland, Norway or Sweden

## Slide 8: Description of Activities
Online Service access
Allows parties to access and view Online Service
Parties may start testing Online Service functionalities
Connectivity test
eSett needs to establish a machine-to-machine connectivity with all involved parties
  Established with Energinet
May take a lot of time due to firewalls and number of parties
Data flow test
Readiness to send and receive positively acknowledged messages to/from eSett
End-to-End test
Verification of data flows and processes from business perspective
Data makes sense and is correct
Parallel run
Reporting of production values to eSett’s test environment
Verification of results

## Slide 9: Structure Establishment and Management

## Slide 10: Structure Establishment and Management
Phases/activities:
Verification (4a)
Continuous updates (4b & 4d)
Freeze period 1 (4c)
Verification and updates in production environment (4e)
Freeze period 2 (4f)
After go-live
eSett Test Environment
eSett Production Environment
Structure data updates
4f. Freeze period 2
4d. Structure data
continuous updates
4c. Freeze period 1
4b. Structure data
continuous updates
4a. Structure verification
4f. Freeze period 2
4e. Structure data
continuous updates
4c. Freeze period 1

## Slide 11: Initial Verification
Initial structural data for Danish market has been compiled by Energinet and added to test environment by eSett
BRPs need to verify their own data in the Online Service (chapter 7.1.2), for example:
  Company & market party details
  Balance responsibilities over retailers (RBRs)
  Channel of electronic communication
  Time series for consumption, production, trades etc.
  Regulation objects
  Users
Deadline for verification has been set to Friday 05.06.2020
  Confirmation to eSett’s customer service once you have verified the structures
11

## Slide 12: Continuous Updates
Structural data needs to be continuously updated – it will be used later in go-lives.
eSett and Energinet will update in co-operation the master data, such as:
  Market participants
  Areas (MGAs)
  Regulation Objects
Energinet DataHub is responsible for updating consumption, production and MGA imbalance retailer information
BRPs have to update the data that’s on their responsibility:
  Own information (contacts, users etc.)
  BRP-Retailer relations (RBRs)
  Bilateral trades
    Changes require counterparty approval in Online Service

## Slide 13: Structures from Test to Production
eSett will import structural information from test environment to production
This will be done in two phases
  Import of market participants and structures for Capacity Reserve go-live – August 2020
  Import of market participants and structures for imbalance settlement go-live – October 2020
How does this affect BRPs?
BRPs are expected to verify their structures after import(s)
After 2nd import, BRPs need to keep their structures up-to-date in two environments:
  Test environment (4d) – for successful testing and parallel run
  Production environment (4e) – for successful go-live
13

## Slide 14: Freeze Periods
During freeze periods there are restrictions to structural changes.
1st Freeze period – 01.09.2020 to 11.10.2020
Changes in market participants – e.g. new ones, mergers of existing ones etc.
MGA and MBA definition changes
Retailer Balance Responsibility contracts (RBRs)
2nd Freeze period – 02.01.2021 to 14.02.2021
Same restrictions as in the 1st period
Also, changes to following structures should be avoided
  Production
  Consumption
  MGA Imbalance Retailers
  Bilateral Trades
  PX Market Trades
Purpose is to ensure smooth go-live periods without extra workload

## Slide 15: After Go-Live
After the 2nd go-live and 2nd freeze period, everyone should finally start their “normal operations”.
Should be similar to the previous continuous updates activities
eSett has the “master data” for Denmark for imbalance settlement in Online Service
Keeping the structures up-to-date in test environment is no longer necessary
Similar operations as with Finland, Norway and Sweden

## Slide 16: Agreements

## Slide 17: Agreements
Agreements
6. Agreements *
7b. Go-live
7a. Capacity Reserves GL

## Slide 18: Agreements with Danish BRPs
eSett has prepared new agreement templates to support Denmark integration.
Updated templates are available in eSett’s website
Changes are quite minimal and all the same agreements are still needed:
Imbalance settlement agreement
Pledged cash account agreement + MT101 (direct debit) & MT940 (account statements)
Balance agreement with Energinet
Standard settlement instructions.
Also the appendices (Fees, Collaterals and NBS Handbook) of imbalance settlement agreement have been or will be updated.
Collaterals are not used in Denmark
If BRP is already active in Finland, Norway or Sweden, Imbalance settlement agreement is already valid.
The need for agreements is checked case by case.

## Slide 19: Timeline for the Agreements
May
eSett will prepare agreements and instructions for each BRP that’s active in Denmark
Agreement packages will be sent out to provided contact persons
June-August
BRPs to establish settlement accounts and sign the agreements
Signed agreements and other required documents should be sent back to eSett by 31st of August
  Especially important for the BRPs that are active in the capacity reserve market and will be part of the 1st go-live
August-September
eSett will go through and sign the agreements
Each party should receive their original copies of the signed agreements

## Slide 20: Communication and Documentation

## Slide 21: Communication
I
II*
III*
II
III
Webinar (BRP)

## Slide 22: Webinars to BRPs
eSett has planned to keep three webinars for the BRPs:
Webinar 1 – 30.4.2020 Introduction Agreements, accounts and banks Online Service Structures – verification and updating
Webinar 2 – August*/October Data interchange Test status Parallel run
Webinar 3: September*/January Go-Live readiness and preparations Summary
Only for BRPs participating in capacity reserves go-live
22

## Slide 23: Other Communication
“Denmark Go-Live” section on eSett’s website.
Main source of up-to-date information
Latest version of commissioning plan for BRPs
Denmark newsletter subscription
Denmark specific news
Denmark newsletter
Information about the progress of integration project
Major updates in commissioning plan
Other relevant news

## Slide 24: Documentation
Commissioning plan for BRPs
The main document for commissioning
Will be continuously updated
  Latest version always available in eSett’s website
  Major updates are announced in Denmark newsletter
Contains detailed instructions for all activities, documents, systems, test practices etc.
Has some supportive documents:
  Connectivity troubleshooting
  Test document – instructions for testing of Online Service and data flows
  Data flow validation reason texts
Also NBS Handbook has been updated (version 2.4) to cover Denmark specific information.

## Slide 25: New Features

## Slide 26: New Features
eSett’s next major version upgrade (version 20) has a support for Denmark integration.
The version also contains several new features that are part of Denmark integration:
Capacity reserves
  Will be taken into use in Denmark starting from 1st of October 2020
Merged production
  Might be taken into use in Norway in mid-September 2020
  Will be taken into use in Denmark starting from 1st of February 2021
Flex settled consumption
  Will be taken into use in Denmark starting from 1st of February 2021
  New measurement type for consumption – only used in Denmark

## Slide 27: Capacity Reserves
The first go-live of Denmark integration is about capacity reserves
Energinet purchases reserve capacity from market participants
Market participants are compensated for the reserved capacities
Energinet will report the capacities to eSett
eSett will handle the invoicing on behalf of Energinet
  Very similar to what is done with activated reserves
Online Service will have a new section for BRPs: Input Data » Others » Capacity Reserves
Capacity reserves are defined per BRP, MBA and Balancing Sub Service
  For example: BRP01 – DK1 – FRR-A
Not part of imbalance settlement

## Slide 28: Merged Production
A new way to model production alongside with Production Units
Objectives to
  Support integration of Denmark
  Reduce the number of PUs in the system
  Provide an easier way to handle production in the system
Merged Production is not linked to PUs
Can be used to aggregate production of a retailer in MGA instead of having multiple PUs or a virtual PU
Very similar with existing Consumption MEC feature

## Slide 29: Merged Production
Can be taken into use only in countries where datahub is active
  Elhub plans to take this into use mid-September in Norway
  All production in Denmark will be merged production at least until 2022
Can’t be linked to Regulation Objects
MEC creation is handled with same data flow as time series reporting
Production overview example:
From | To | MEC ID | RE | DSO | MBA | MGA | PU | Production Type | PU Type | RO
1.1.2017 | Undefined | PROD001 | RE 01 | DSO 01 | MBA | MGA 01 | PU Name | Normal | Hydro | RO Name
1.9.2020 | Undefined | MEPR001 | RE 01 | DSO 01 | MBA | MGA 01 |  | Minor | Solar | 
9.9.2020 | Undefined | MEPR002 | RE 02 | DSO 01 | MBA | MGA 01 |  | Normal | Wind |